This Appendix was submitted prior to the endline data collection. It details several changes made to the experimental design that were not discussed in the original pre-analysis plan.

Experimental Design Changes

T2:  Environmental Info + Cooperation tools+ Public Monitoring:

In the original pre analysis plan we wrote that public canals would be tested four times within each village. After collecting baseline data, which occurred after the submission of the pre-analysis plan, it became apparent that there was substantial variation within villages in the timing of when farmers would begin their next shrimp crop. Baseline data revealed that a significant number of farmers would commence shrimp cropping in November 2024, while another group would begin in February/March 2025. To accommodate this extended timeline, we adapted the design to include two rounds of public testing in 2024 and two rounds in 2025. The first round of testing in each cycle is planned before the start of the shrimp season for as many farmers as possible. All shrimp farmers within our village sample will receive the test results via SMS and their community Zalo group to ensure widespread dissemination of the information.

T3:  Environmental Info + Cooperation tools +  Public Monitoring AND Private Testing:

As discussed above from baseline data we observe significant heterogeneity within villages in when farmers would start their next shrimp crop. Similar to the T2, we decided to modify the design and conduct two rounds of private testing for farmers who started in 2024 and two rounds of private testing for farmers who started in 2025. Before each private testing round, we contact farmers by phone to confirm shrimp availability and schedule appointment for shrimp collection. To minimise costs we set a rule that private testing in a village would only take place if the village was assigned to T3 and if at least 4 farmers were actively working on a shrimp crop and their shrimps age less than 70 days at the time of testing.  The results of private testing will be sent to individual farmers via SMS only.