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1. Introduction and context
On October 18th, 2019, a major social unrest started to take place in Chile. This has affected the normal functioning of the country, in all areas, and in all its regions. As of today, this situation is still ongoing and it does not seem to come to an end in a near future. One of the main affected areas is the Biobio Region, where our intervention takes place.

2. Implications for implementation
Following the schedule of the implementation of the experimental design, our intervention was expected to end on December 13th, 2019. Although the intervention did follow the proposed schedule before the unrest, the administration of the intervention has suffered delays as a consequence of the unrest, which affected the management of the schools (e.g., lessons canceled by the educational institutions, teachers’ strikes, absence of students in response to parents’ concerns, etc.). This situation was an unexpected event out of control of the researchers involved. Notwithstanding the difficult situation, the researchers have managed to continue implementing the program keeping the contents and activities exactly as planned, but with some flexibility in terms of the frequency of the lessons. As of today, the program has been finalized in 11 out of 15 treated schools, including the ex-post survey. Additionally, the lessons contained in the program has been completed in 13 out of 15 schools (in the remaining 2 schools only the final lesson is missing). The research team has re-scheduled the closing activity of the program in the remaining 4 treated schools, and, if nothing more happens, this will take place complying with the deadline established in the published version of the pre-analysis plan (December 13th).[footnoteRef:1] A summary of the program administration is displayed in Table S1. [1:  Notwithstanding the good disposition of the school principals and students, because of the uncertainty people are experiencing in response to this crisis, we cannot rule out the possibility of not being able to administrate the closing activity in some of the remaining schools (or missing an important share of students), in the current academic year. In case such extreme event takes place, the principals of the schools will allow us to conduct the closing activity of the program at the beginning of the next academic year (i.e., March 2020). This activity will include a summary lecture, followed by the closing activity and the ex-post survey.  ] 

   
Regarding the control group, the ex-post survey has been applied to 11 out of 15 schools. Similar to the treatment group, the closing activity has been re-scheduled so that it takes place during December 2019, and a similar strategy will be followed in case the current circumstances prevent us from administering the survey. 


          Table S1. Timeline of the intervention
	School ID
	Treatment status
	No. students
	Lectures completed before the shock
	Program completed before the shock

	T1
	Treatment
	35
	Yes
	No

	T2
	
	33
	Yes
	No

	T3
	
	63
	No
	No

	T4
	
	57
	No
	No

	T5
	
	31
	No
	No

	T6
	
	32
	Yes
	No

	T7
	
	46
	No
	No

	T8
	
	19
	No
	No

	T9
	
	45
	Yes
	No

	T10
	
	24
	Yes
	Yes

	T11
	
	73
	Yes
	No

	T12
	
	66
	Yes
	No

	T13
	
	67
	Yes
	No

	T14
	
	30
	Yes
	Yes

	T15
	
	45
	No
	No

	C1
	Control
	23
	N/A
	No

	C2
	
	36
	N/A
	No

	C3
	
	54
	N/A
	No

	C4
	
	23
	N/A
	No

	C5
	
	90
	N/A
	No

	C6
	
	150
	N/A
	No

	C7
	
	44
	N/A
	No

	C8
	
	18
	N/A
	No

	C9
	
	18
	N/A
	No

	C10
	
	54
	N/A
	No

	C11
	
	76
	N/A
	No

	C12
	
	36
	N/A
	No

	C13
	
	30
	N/A
	Yes

	C14
	
	106
	N/A
	No

	C15
	
	79
	N/A
	No


            Source: Internal data.   

3. Implications for data analysis
To date, we have not conducted any exploratory analysis of the ex-post data that has been collected, the data has actually not been digitized yet. The research team will not analyze anything until all data has been collected.

Because the social unrest in Chile may undermine the environmental preferences of individuals, it is potentially important to control for the potential effects of the strikes on both children and parents’ behavior in the econometric analysis. We do hypothesize that the potential negative effects of the strikes will be larger for parents, compared with children. An explanation for that is the increasing levels of stress that adults experience as a consequence of the violence and insecurity in their surroundings, in addition to the fear of experiencing economic/wellbeing losses (e.g., unemployment, loss of assets, food/medicine shortages, etc.).  Consequently, the estimated ATE will be regarded as a lower-bound effect of the intervention. To address the potential effects of the strikes on the behavior of children and parents, we propose including two set of dummy variables. The first dummy variable will control for schools where the closing activity took place before the beginning of the shock (i.e., 2/15 schools). This will be done by adding an interaction term post*treated*closing. We do expect a positive interaction term. The second dummy variable will account for the schools that completed the lessons embedded in the program before the shock took place (i.e., 9/15 schools). This will be done by adding an interaction term post*treated*lecturing. We do expect a positive interaction term, but with lower in magnitude compared with the previous interaction term.

Alternatively, we propose conducting robustness checks by removing both treated and control schools closing the program before the start of the shock (i.e., 2 treated and 1 control schools, respectively). This strategy is based on the assumption that both treated and control schools have been equally affected by the social unrest in the country. We propose following a similar strategy to account for the effects of a late closing of the intervention (i.e., schools finishing in early march due to early ending of the academic year). Other situations that may occur after the submission of this document will be addressed by conducting an exploratory analysis.  
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